## Slide 1: Watermelon 0.1
Purpose of this release
  Change everything under the hood; recapitulate the old pipeline
    Learn the old pipeline
    Learn the new technologies
  Implement sustainable development practices
Notes: abhasi

## Slide 2: Legacy -> Watermelon did change some things
 | Legacy | Watermelon
# scripts | 26 | 15
~ Lines of Code “main” | 2400 | 600
~ Lines of Code total | 6400 | 3200
Automated tests | 0 | 150
More modularity in implementation and results
Better parallelization
Better restartability (errors, crashes)
Simpler config for multiple analyses
(Slightly) better reports [flipped comparisons, run details]
Version control, automated tests, paired development
Positioned to add new capabilities
Notes: cgates

## Slide 3
Version 0.1
SE analysis
QC (Fastqc)
Quality and end trimming (Cutadapt)
Genome + Transcriptome alignment (Tophat)
ReadCounts (HTSeq)
Gene and isoform differential expression (Cuffdiff, Cummerbund)
Cuffdiff Excel files (now flipped!)
Testing and release
Stranded
Multiple phenotypes support
hg19
mm10
Version 0.2
Gene differential expression(DESeq2)workflow (in progress)
DESeq2 report/plots (in progress)
Support for concat reads
Paired-end analysis
Bug fixing
iPathwayGuide results
Version x
ce10
WS195, Zv9
GRCz10, dm6
Version y
Better QC (FastQScreen,MultiQC)
Better alignment( STAR,HISAT2)
Better diffex (EdgeR, Limma, VOOM)
Other genomes
Legacy retired
Release
Functionality
Genomes
Comp3
Comp5
Flux
GRCh37
GRCm38
Rn7, Rnor_6.0
Better reporting (MultiQC, Comprehensive experiment report)
Spec comprehensive experiment report
Extended support for multiple runs
Updated deliverable doc
Maintenance doc
Module-based genome references/annotations
Continued support for cuffdiff
Research alternate isoform diffex
Adjusted intron length
Release:
2/6/2017
Release: TBD
Notes: abhasi

## Slide 4: Lessons learned
It’s good that …
  We are using Snakemake
  We addressed multiple phenotype analyses
  We deferred DESeq2
  We hired CJ
Given hindsight, next time …
  Shorter release cycle
  More interim show & tells
  More feedback from “Bridget”
  Plan for unanticipated problems/opportunities
Notes: cgates

## Slide 5: Next steps & Questions
Rollout
  Soft launch to Becky (and CJ, Rich)
    Orientation next week
    SE, human/mouse project in Watermelon
Continuing development
  Add PE, DESeq2
  Better setup (e.g. multiples seq runs)
  Better progress monitoring
  Support and bug fixes
General release March
  Legacy retired
Notes: abhasi

## Slide 7
legacy
FastQ
samples.txt
comparisons.txt
config.ini
Command-line options
trimming
genomic/transcriptome alignment
watermelon
FastQ
config.yaml
watermelon-init